## Gantt Chart w % Complete
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Semester
| Customer Needs | 2018-09-14 | 14 | 2018-09-21 | 8 | 8 | 0 | Lead: Oscar | 100%
| Work Breakdown Structure | 2018-09-14 | 14 | 2018-09-21 | 8 | 8 | 0 | Lead: Jacob | 100%
| VDR1 | 2018-09-28 | 28 | 2018-10-02 | 5 | 5 | 0 | All | 100%
| Functional Decomposition | 2018-09-28 | 28 | 2018-09-28 | 1 | 1 | 0 | Lead: Jacob & Oscar | 100%
| Targets | 2018-09-29 | 29 | 2018-10-19 | 21 | 21 | 0 | Lead: John | 100%
| Advisor Meeting October | 2018-09-30 | 30 | 2018-10-31 | 32 | 32 | 0 | All | 100%
| Concept Generation | 2018-10-01 | 1 | 2018-10-29 | 29 | 29 | 0 | All | 100%
| Innolevation: Stage 1 Application Deadline | 2018-10-02 | 2 | 2018-11-02 | 32 | 32 | 0 | Jacob | 100%
| Concept Selection | 2018-10-03 | 3 | 2018-11-02 | 31 | 31 | 0 | All | 100%
| Bill of Material | 2018-10-04 | 4 | 2018-11-09 | 37 | 37 | 0 | Oscar | 100%
| VDR2 | 2018-10-05 | 5 | 2018-11-15 | 42 | 42 | 0 | Oscar | 100%
| Risk Assessment | 2018-10-06 | 6 | 2018-11-16 | 42 | 42 | 0 | Lead: Oscar | 100%
| Advisor Meeting November | 2018-10-07 | 7 | 2018-11-28 | 53 | 53 | 0 | All | 100%
| VDR 3 Poster Presentation | 2018-10-08 | 8 | 2018-12-06 | 60 | 60 | 0 | Lead: Oscar | 100%
| Spring Project Plan | 2018-10-09 | 9 | 2018-12-07 | 60 | 60 | 0 | Jacob | 100%
| Sponsor Meeting | 2018-10-10 | 10 | 2018-11-30 | 52 | 52 | 0 | All | 100%
Second Semester
| Innolevation: Stage 2 Business Model Canvas | 2019-01-06 | 6 | 2019-01-14 | 9 | 9 | 0 | Oscar | 100%
| Advisor Meet & Greet | 2019-01-07 | 7 | 2019-01-11 | 5 | 5 | 0 | All | 100%
| Abstract | 2019-01-08 | 8 | 2019-01-11 | 4 | 4 | 0 | Oscar & Jacob | 100%
| Budget Update | 2019-01-09 | 9 | 2019-01-18 | 10 | 10 | 0 | Oscar & Jacob | 100%
| Web Master | 2019-01-10 | 10 | 2019-01-18 | 9 | 9 | 0 | Oscar | 100%
| Advisor Meeting 1 | 2019-01-11 | 11 | 2019-01-31 | 21 | 21 | 0 | All | 100%
| Web Page Development | 2019-01-12 | 12 | 2019-02-01 | 21 | 21 | 0 | Oscar | 100%
| Innolevation: Stage 3 Final Business Model Canvas | 2019-01-13 | 13 | 2019-02-06 | 25 | 25 | 0 | Oscar | 100%
| Innolevation: Semi-Final Presentation Judging | 2019-01-14 | 14 | 2019-02-08 | 26 | 26 | 0 | All | 100%
| Shark Tank Application | 2019-01-15 | 15 | 2019-02-08 | 25 | 25 | 0 | Oscar | 100%
| DR5 (Senior Design Presentation) | 2019-01-16 | 16 | 2019-02-18 | 34 | 34 | 0 | All | 100%
| Advisor Meeting 2 | 2019-01-17 | 17 | 2019-02-28 | 43 | 43 | 0 | All | 100%
| Risk Assessment | 2019-01-18 | 18 | 2019-02-28 | 42 | 42 | 0 | All | 100%
| Web Page Update 1 | 2019-01-19 | 19 | 2019-03-01 | 42 | 42 | 0 | Oscar | 100%
| Shark Tank Round 2 Submission | 2019-01-20 | 20 | 2019-03-08 | 48 | 48 | 0 | Oscar | 100%
| Shark Tank Preliminary Round Business Pitch | 2019-01-21 | 21 | 2019-03-08 | 47 | 47 | 0 | All | 100%
| DR6 (Senior Design Presentation) | 2019-01-22 | 22 | 2019-03-25 | 63 | 63 | 0 | All | 100%
| Operation Manual | 2019-01-23 | 23 | 2019-03-29 | 66 | 66 | 0 | Lead: John | 100%
| Web Page Update 2 | 2019-01-24 | 24 | 2019-04-05 | 72 | 72 | 0 | Oscar | 100%
| Engineering Design Day | 2019-01-25 | 25 | 2019-04-18 | 84 | 84 | 0 | All | 100%
| Final Report | 2019-01-26 | 26 | 2019-04-26 | 91 | 91 | 0 | Lead: Oscar | 100%
| Protyope Demo | 2019-01-27 | 27 | 2019-04-26 | 90 | 90 | 0 | All | 100%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Basic Gantt Chart
GANTT CHART TEMPLATE
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 0 | 4 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 2018-01-11 | 3 | 4 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 6 | 6 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 2018-01-19 | 9 | 6 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 2018-01-23 | 12 | 7 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 2018-01-12 | 4 | 4 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 2018-01-19 | 7 | 8 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 2018-01-19 | 12 | 3 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 2018-01-26 | 17 | 5 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 2018-01-19 | 10 | 5 | Nathan | 100%
| Reserve Room | 2018-01-22 | 2018-01-23 | 17 | 2 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 2018-01-26 | 17 | 5 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 2018-01-29 | 21 | 4 | Michael | 40%
| Create Invitations | 2018-01-22 | 2018-01-25 | 17 | 4 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 2018-01-24 | 10 | 10 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 2018-01-30 | 20 | 6 | Meredith | 80%
| Update Messaging | 2018-01-24 | 2018-01-30 | 19 | 7 | Michael | 60%
| Publish Calculator | 2018-01-30 | 2018-01-31 | 25 | 2 | Rachel | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Manual Chart
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 2 | Nathan | 100%
|  |  |  | 0 | Meredith | 80% | bar: WEEK 2 M to WEEK 2 T
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 4 | Brandon | 60% | bar: WEEK 1 F to WEEK 2 Th
| Build Landing Page | 2018-01-14 | 2018-01-19 | 5 | Michael | 40% | bar: WEEK 2 T to WEEK 3 M
| Code Review Landing Page | 2018-01-17 | 2018-01-21 | 3 | Rachel | 20% | bar: WEEK 2 Th to WEEK 3 W
| Promote Landing Page | 2018-01-20 | 2018-01-23 | 2 | Annie | 10% | bar: WEEK 3 T to WEEK 3 Th
Second Sample Project
| Write Promotional Email | 2018-02-05 | 2018-02-08 | 4 | Nathan | 100%
| Design Promotional Email | 2018-02-08 | 2018-02-13 | 4 | Meredith | 80%
| Send Promotional Email to Contacts | 2018-02-11 | 2018-02-16 | 5 | Michael | 60%
| Analyze Results of Email Campagin | 2018-02-14 | 2018-02-23 | 8 | Annie | 40%
Third Sample Project
| Plan Agenda for Team Meeting | 2018-03-05 | 2018-03-08 | 4 | Rachel | 100%
| Reserve Room and Resources for Meeting | 2018-03-08 | 2018-03-13 | 4 | Michael | 80%
| Finalize Team Presentation | 2018-03-11 | 2018-03-16 | 5 | Brandon | 60%
| Review & Approve Presentation | 2018-03-14 | 2018-03-19 | 4 | Meredith | 40%
| Create Invitations for Meeting | 2018-03-17 | 2018-03-21 | 3 | Annie | 20%
| Setup Room for Meeting | 2018-03-20 | 2018-03-25 | 4 | Nathan | 10%
Fourth Sample Project
| Rewrite Code for Online Calculator | 2018-04-05 | 2018-04-08 | 2 | Nathan | 100%
| Code Review Updated Calculator | 2018-04-08 | 2018-04-10 | 2 | Meredith | 80%
| Update Messaging for Calculator | 2018-04-11 | 2018-04-16 | 4 | Michael | 60%
| Publish New Calculator to Site | 2018-04-14 | 2018-04-18 | 3 | Rachel | 40%
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])