## Sheet1
Date: 11/8/2018
| Item # | Category | Item Name | Quantity | Material | Weight (lb) | Order Status | Vendor Name | Part Number | Website | Lead Time (Days) | Cost Per Item ($) | Projectd Shipping Cost ($) | Quantity Shipped | Tax | Projected Cost ($)
| 1 | Product | Proximity Sensor (Capacitive) | 2 | ABS | 0.36 | Completed | Grainger | 2AKD8 | https://www.grainger.com/ | 0 | 143.33 | 0 | 2 | E | 286.66
| 2 | Product | Global Limit Switch | 2 | Zinc Die Cast/Stainless Steel | 1.05 | Completed | Grainger | 12U922 | https://www.grainger.com/ | 0 | 95.53 | 0 | 2 | E | 191.06
| 3 | Product | Solenoid | 2 | - | 1.4 | Completed | Grainger | 4X241 | https://www.grainger.com/ | 0 | 39.35 | 0 | 2 | E | 78.7
| 4 | Product | Photoelectric Sensor | 2 | PBT | 0.23 | Completed | Grainger | 32J327 | https://www.grainger.com/ | 0 | 81.75 | 0 | 2 | E | 163.5
| 5 | Product | Proximity Switch (Inductive) | 2 | Stainless Steel | 0.39 | Completed | Grainger | 40HT96 | https://www.grainger.com/ | 0 | 95 | 0 | 2 | E | 190
| 6 | Product | Rotary Encoder | 1 | - | 0.4 | Not Ordered | Grainger | 11M881 | https://www.grainger.com/ | 2 | 230.5 | 0 | 1 | E | 230.5
| 7 | Material | Bins | 6 | Plastic | - | Not Ordered | - | - | - | 1 | - | 0 | 4 | - | 10
| 8 | Product | Conveyor Belt | 2 | - | 110 | Completed | McMaster-Carr | 5734K252 | https://www.mcmaster.com/conveyors | 0 | 1563.24 | 0 | 2 | E | 3126.48
| 9 | Labor | Sensor Mount | 2 | PLA Filament | - | In Progress | - | - | https://innovation.fsu.edu/ | 2 | 0 | 0 | 2 | - | 0
| 10 | Labor | PLC Controller Mount | 1 | PLA Filament | - | In Progress | - | - | https://innovation.fsu.edu/ | 2 | 0 | 0 | 1 | - | 0
| 11 | Product | Programming Logic Controller | 2 | - | 1.5 | Completed | Allen-Bradley | 1769-L18ER-BB1B | https://ab.rockwellautomation.com/ | 0 | 2560 | 0 | 2 | E | 5120
| 12 | Labor | Conveyor Diverter Bar | 1 | PLA Filament | - | In Progress | - | - | https://innovation.fsu.edu/ | 2 | 0 | 0 | 1 | - | 0
| Total |  |  | 25 | [11 empty] | 9396.9