## Sheet1
Simulated Assembly Line and Process Workstation
Tallahasse Community College
FAMU-FSU CoE ME Department
TASK NAME | ASSIGNED TO | START DATE | END/DUE DATE | DURATION | % DONE | DESCRIPTION | PRIORITY | SPRINT/MILESTONE
Abstract | David, Cheyenne, Bolu | 2019-01-18 | 2019-02-08 | 21 | 100 |  |  | Phase 1
Webpage Dev & Update | Bolu | 2019-01-18 | 2019-04-05 | 77 | 75 |  |  | Phase 1
3d Print Sensor Mount | David | 2019-01-25 | 2019-02-05 | 11 | 100 |  |  | Phase 1
Mount sensors | David, Bolu | 2019-02-05 | 2019-02-14 | 9 | 100 |  |  | Phase 1
Assemble conveyor belts | Cheyenne, Natajaah, JoEll | 2019-02-12 | 2019-02-14 | 2 | 100 |  |  | Phase 1
High Resolution Graphic | David | 2019-01-25 | 2019-02-22 | 28 | 100 |  |  | Phase 1
DR5 | Everybody | 2019-02-14 | 2019-02-26 | 12 | 100 |  |  | Phase 2
Risk Assessment | All, except David | 2019-02-20 | 2019-02-28 | 8 | 60 |  |  | Phase 2
Order servo motor | Bolu, Cheyenne | 2019-02-14 | 2019-02-28 | 14 | 50 |  |  | Phase 2
3d print diverter arm | Cheyenne | 2019-02-14 | 2019-02-28 | 14 | 25 |  |  | Phase 2
Conference paper identification | Everybody | 2019-02-22 | 2019-03-01 | 7 | 50 |  |  | Phase 2
Acquire bins for sorting | Everybody | 2019-02-14 | 2019-03-01 | 15 | 25 |  |  | Phase 3
Acquire objects to be sorted | Everybody | 2019-02-14 | 2019-03-01 | 15 | 25 |  |  | Phase 3
Poster | Everybody | 2019-02-28 | 2019-03-08 | 8 | 0 |  |  | Phase 3
Acquire PLC | David, Cheyenne, Bolu | 2019-01-28 | 2019-03-08 | 39 | 50 |  |  | Phase 3
Mount motor to conveyor belt | Bolu, Natajaah, JoEll | 2019-03-04 | 2019-03-08 | 4 | 0 |  |  | Phase 3
Connect arm to motor | Cheyenne | 2019-03-04 | 2019-03-08 | 4 | 0 |  |  | Phase 3
Connect sensors to PLC | Bolu, Natajaah, JoEll | 2019-03-04 | 2019-03-08 | 4 | 50 |  |  | Phase 3
Connect servo motor to PLC | Bolu, Natajaah, JoEll | 2019-03-04 | 2019-03-08 | 4 | 25 |  |  | Phase 3
Connect conveyor belts to PLC | Bolu, Natajaah, JoEll | 2019-03-04 | 2019-03-12 | 8 | 70 |  |  | Phase 3
DR6 | Everybody | 2019-02-28 | 2019-03-25 | 25 | 0 |  |  | Phase 4
Conference paper | Everybody | 2019-03-07 | 2019-03-29 | 22 | 0 |  |  | Phase 4
Operational Manual | Everybody | 2019-03-07 | 2019-03-29 | 22 | 0 |  |  | Phase 4
Engineering Design Day | Everybody | 2019-03-21 | 2019-04-11 | 21 | 0 |  |  | Phase 4
Prototype demo | Everybody | 2019-03-28 | 2019-04-26 | 29 | 0 |  |  | Phase 4
Final report | Everybody | 2019-03-21 | 2019-04-26 | 36 | 0 |  |  | Phase 4
End of project | Everybody | 2018-08-21 | 2019-04-26 | 248 | 60 |  |  | Phase 4
Phase 4