## Spring Plan
[7 empty] | Project Instructor: Shayne McConomy |  |  |  | Project: Team 515 | [18 empty] | Date: | 2021-12-01
Project Objective: Develop and test a nuclear reactor canister for use in a nuclear propulsion system engine
Objectives | [7 empty] | Major Tasks |  |  | Project Completed By: March 30, 2022 | [17 empty] | Owner / Priority
✓ | [6 empty] | 1 | Spring Semester Initial Meeting |  |  | ™ | [21 empty] | ✓
✓ | [6 empty] | 2 | Spring Work Breakdown Structure |  |  | ™ | ™ | [20 empty] | ✓
|  | ✓ |  |  |  |  | 3 | Finalize General Design |  |  | ™ | ™ | [20 empty] | ✓
|  |  | ✓ |  |  |  | 4 | CAD of General Design |  |  | ™ | ™ | [20 empty] | ✓
|  |  | ✓ |  |  |  | 5 | CFD Analysis of Model |  |  | ™ | ™ | [17 empty] | ✓ |  | ✓
[6 empty] | ✓ | 6 | Update Bill of Materials |  |  | ™ | ™ | [17 empty] | ✓ |  | ✓
|  |  |  | ✓ |  |  | 7 | Order Components |  |  |  | ™ | ™ | [19 empty] | ✓
✓ | [6 empty] | 8 | Apply For Graduation (Open) |  |  |  |  | ™ | [19 empty] | ✓
|  | ✓ |  |  |  |  | 9 | CAD of Nitrogen Flow |  |  |  | ™ | ™ | [19 empty] | ✓
|  |  | ✓ |  |  |  | 10 | CFD Analysis of Nitrogen Flow |  |  |  | ™ | ™ | [17 empty] | ✓ | ✓
[6 empty] | ✓ | 11 | Assembly and Begin General Testing |  |  |  |  | ™ | ™ | [14 empty] | ✓ |  | ✓
[6 empty] | ✓ | 12 | Update Sponsor |  |  |  |  | ™ | ™ | [14 empty] | ✓ | ✓
| ✓ | [5 empty] | 13 | Begin Design Refinment and Additions |  |  |  |  | ™ | ™ | [15 empty] | ✓ |  | ✓
|  |  | ✓ |  |  |  | 14 | Apply For Graduation (Closes) |  |  |  |  | ™ | ™ | [15 empty] | ✓ |  | ✓
|  |  | ✓ |  |  |  | 15 | Finalize Updated Design | [5 empty] | ™ | ™ | [13 empty] | ✓ |  |  | ✓
|  |  | ✓ |  |  |  | 16 | CAD of Updated Design |  |  | ™ | ™ | ™ | ™ | ™ | [13 empty] | ✓ |  | ✓
|  |  |  | ✓ |  |  | 17 | Update Bill of Materials |  |  | ™ | ™ | ™ | ™ | ™ | [17 empty] | ✓
|  |  | ✓ |  |  |  | 18 | Order Components | [7 empty] | ™ | ™ | [12 empty] | ✓ | ✓
[5 empty] | ✓ |  | 19 | Assemble with All New Components | [5 empty] | ™ | ™ | ™ | ™ | ™ | [10 empty] | ✓ |  | ✓
[6 empty] | ✓ | 20 | Begin Testing New Model | [6 empty] | ™ | ™ | ™ | ™ | [14 empty] | ✓
| ✓ | [5 empty] | 21 | Update Sponsor | [7 empty] | ™ | ™ | ™ | ™ | [9 empty] | ✓ |  |  | ✓
[5 empty] | ✓ |  | 24 | Final Testing of Product | [9 empty] | ™ | ™ | ™ | ™ | [11 empty] | ✓
| ✓ | [5 empty] | 25 | Finalize Project For Presentation | [11 empty] | ™ | ™ | ™ | [7 empty] | ✓ | ✓
| ✓ | [5 empty] | 26 | Engineering Design Day | [14 empty] | ™ | [9 empty] | ✓
|  | ✓ |  |  |  |  | 27 | Last Day of Classes | [17 empty] | ™ | [6 empty] | ✓
|  | ✓ |  |  |  |  | 28 | Final Exam Week | [18 empty] | ™ | [5 empty] | ✓
|  | ✓ |  |  |  |  | 29 | Graduation | [19 empty] | ™ |  |  |  |  | ✓
[9 empty] | # People working on the project: | 4
Homework | Presentation | Academic | Design | Documentation | Assembly | Testing |  |  |  |  | 1-3-22 | 1-10-22 | 1-17-22 | 1-24-22 | 1-31-22 | 2-2-22 | 2-14-22 | 2-21-22 | 2-28-22 | 3-7-22 | 3-14-22 | 3-21-22 | 3-28-22 | 4-4-22 | 4-11-22 | 4-18-22 | 4-25-22 | 4-30-22 | Mac Borngesser | Braden Dukes | Jaxon Stadelnikas | Brian McGough | All Members
Millions
[35 empty] | Budgeted | Expended
[34 empty] | #REF! | 0 | 0
[34 empty] | #REF! | 0 | 0
[34 empty] | #REF! | 0 | 0
Major Tasks
Summary & Forecast
Objectives
Target Dates
Costs