## Project Timeline
PROJECT TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE | Position Adjusted | Date adjusted | Milestone adjusted
2022-01-05 | Classes Begin | 25 | 0 | 25 | 2022-01-05 | Classes Begin
2022-01-07 | Meet with Sponsor | -8 | 0 | -8 | 2022-01-07 | Meet with Sponsor
2022-01-14 | Meet with John Kynoch | -13 | 0 | 10 | 2022-01-14 | Analyze Pump Optimization Data
2022-01-14 | Analyze Pump Optimization Data | 10 | 0 | -13 | 2022-01-14 | Meet with John Kynoch
2022-01-20 | Calculate ICRB Pipe Cost | -30 | 0 | -30 | 2022-01-20 | Calculate ICRB Pipe Cost
2022-01-21 | Order all parts for validation technique | 18 | 0 | -13 | 2022-01-14 | Meet with John Kynoch
2022-01-28 | January Advisor Meeting | 28 | 0 | -30 | 2022-01-20 | Calculate ICRB Pipe Cost
2022-01-28 | Have a 1st Draft for Website Done | -20 | 0 | -30 | 2022-01-20 | Calculate ICRB Pipe Cost
2022-02-04 | Foundation for the 3-D Model of Validation Done | 5 | 0 | 18 | 2022-01-21 | Order all parts for validation technique
2022-02-08 | Meet with Sponsor | -10 | 0 | -20 | 2022-01-28 | Have a 1st Draft for Website Done
2022-02-11 | Finalize Recomendation for Pump Optimization | 35 | 0 | 35 | 2022-02-11 | Finalize Recomendation for Pump Optimization
2022-02-18 | Finalize Recomendation for ICRB Chillwater Transport | -30 | 0 | -30 | 2022-02-18 | Finalize Recomendation for ICRB Chillwater Transport
2022-02-25 | February Advisor Meeting | -15 | 0 | 5 | 2022-02-04 | Foundation for the 3-D Model of Validation Done
2022-03-01 | Meet with Sponsor | 20 | 0 | 28 | 2022-01-28 | January Advisor Meeting
2022-03-08 | Finalize 3-D Model | 15 | 0 | -15 | 2022-02-25 | February Advisor Meeting
2022-03-25 | March Advisor Meeting | 30 | 0 | -10 | 2022-02-08 | Meet with Sponsor
2022-03-25 | Finish Fabricating Validation Technique | -20 | 0 | 35 | 2022-02-11 | Finalize Recomendation for Pump Optimization
2022-04-01 | Engineering Design Day | 20 | 0 | -15 | 2022-04-25 | Finals Week
2022-04-25 | Finals Week | -15 | 0 | -30 | 2022-02-18 | Finalize Recomendation for ICRB Chillwater Transport
2022-04-30 | Graduation | 15 | 0 | 15 | 2022-04-30 | Graduation
2022-04-30 | Graduation | 15 | 0 | 5 | #NAME?

## Project Data Sorted (hidden)
Sort the dates to populate the timeline in chronological order
|  |  | data analysis | [5 empty] | Actual data to chart, which is fed into the Project Timeline worksheet via hidden columns F-H.
| start row | 5 | TIE BREAK | RANK | DATE | MILESTONE | POSITION | NUM | RANK Sorted | DATE | MILESTONE | POSITION
| last entry | 25 | 21 | 1 | 2022-01-05 | Classes Begin | 25 | 20 | 21 | 2022-01-05 | Classes Begin | 25
|  |  | 20 | 2 | 2022-01-07 | Meet with Sponsor | -8 | 19 | 20 | 2022-01-07 | Meet with Sponsor | -8
|  |  | 18 | 3 | 2022-01-14 | Meet with John Kynoch | -13 | 18 | 19 | 2022-01-14 | Analyze Pump Optimization Data | 10
|  |  | 19 | 3 | 2022-01-14 | Analyze Pump Optimization Data | 10 | 17 | 18 | 2022-01-14 | Meet with John Kynoch | -13
|  |  | 17 | 5 | 2022-01-20 | Calculate ICRB Pipe Cost | -30 | 16 | 17 | 2022-01-20 | Calculate ICRB Pipe Cost | -30
|  |  | 16 | 6 | 2022-01-21 | Order all parts for validation technique | 18 | 15 | 16 | 2022-01-21 | Order all parts for validation technique | 18
|  |  | 14 | 7 | 2022-01-28 | January Advisor Meeting | 28 | 14 | 15 | 2022-01-28 | Have a 1st Draft for Website Done | -20
|  |  | 15 | 7 | 2022-01-28 | Have a 1st Draft for Website Done | -20 | 13 | 14 | 2022-01-28 | January Advisor Meeting | 28
|  |  | 13 | 9 | 2022-02-04 | Foundation for the 3-D Model of Validation Done | 5 | 12 | 13 | 2022-02-04 | Foundation for the 3-D Model of Validation Done | 5
|  |  | 12 | 10 | 2022-02-08 | Meet with Sponsor | -10 | 11 | 12 | 2022-02-08 | Meet with Sponsor | -10
|  |  | 11 | 11 | 2022-02-11 | Finalize Recomendation for Pump Optimization | 35 | 10 | 11 | 2022-02-11 | Finalize Recomendation for Pump Optimization | 35
|  |  | 10 | 12 | 2022-02-18 | Finalize Recomendation for ICRB Chillwater Transport | -30 | 9 | 10 | 2022-02-18 | Finalize Recomendation for ICRB Chillwater Transport | -30
|  |  | 9 | 13 | 2022-02-25 | February Advisor Meeting | -15 | 8 | 9 | 2022-02-25 | February Advisor Meeting | -15
|  |  | 8 | 14 | 2022-03-01 | Meet with Sponsor | 20 | 7 | 8 | 2022-03-01 | Meet with Sponsor | 20
|  |  | 7 | 15 | 2022-03-08 | Finalize 3-D Model | 15 | 6 | 7 | 2022-03-08 | Finalize 3-D Model | 15
|  |  | 5 | 16 | 2022-03-25 | March Advisor Meeting | 30 | 5 | 6 | 2022-03-25 | Finish Fabricating Validation Technique | -20
|  |  | 6 | 16 | 2022-03-25 | Finish Fabricating Validation Technique | -20 | 4 | 5 | 2022-03-25 | March Advisor Meeting | 30
|  |  | 4 | 18 | 2022-04-01 | Engineering Design Day | 20 | 3 | 4 | 2022-04-01 | Engineering Design Day | 20
|  |  | 3 | 19 | 2022-04-25 | Finals Week | -15 | 2 | 3 | 2022-04-25 | Finals Week | -15
|  |  | 1 | 20 | 2022-04-30 | Graduation | 15 | 1 | 2 | 2022-04-30 | Graduation | 15
|  |  | 2 | 20 | 2022-04-30 | Graduation | 15 | 0 | 1 | 2022-04-30 | Graduation | 15