## Sheet1
Item No. | To Be Completed By | Deliverables and Milestones | Decision | Status | Date Complete
1 | 2023-01-13 | Test the Motor in Inventory | Gissel | Complete | 2023-01-10
2 | 2023-01-13 | Acquiring/Developing Code | Gissel | Complete | 2023-01-12
3 | 2023-01-13 | Plan to Account for Undesired Stresses | Joseph | Complete | 2023-01-13
4 | 2023-01-16 | Completed 3D Model | Joseph | Complete | 2023-01-16
5 | 2023-01-20 | CREO Failure Analysis of Every Part | Joseph | Complete | 2023-01-19
6 | 2023-01-27 | Purchase Outsourced Materials | Ibrahim | Complete | 2023-01-30
7 | 2023-02-03 | CREO Part Drawings | Morgan | Complete | 2023-02-05
8 | 2023-02-09 | Virtual Design Review 4 | Megan | Complete | 2023-02-09
9 | 2023-02-10 | Completed Wire Mapping | Gissel | Complete | 2023-02-10
10 | 2023-02-16 | Manufacturing of Parts | Megan | Complete | 2023-02-17
11 | 2023-02-16 | Wiring of Electrical Components | Gissel | Complete | 2023-02-17
12 | 2023-02-17 | Assembly of Prototype | Morgan | Complete | 2023-02-17
13 | 2023-02-23 | Testing the Gearbox | Morgan | Complete | 2023-02-25
14 | 2023-02-23 | Testing the Material | Ibrahim | Complete | 2023-02-25
15 | 2023-02-23 | Virtual Design Review 5 | Megan | Complete | 2023-02-23
16 | 2023-02-27 | Midterm Week | All | Complete | 2023-02-27
17 | 2023-03-02 | Completed Prototype | All | Complete | 2023-03-09
18 | 2023-03-09 | Virtual Design Review 6 | Megan | Complete | 2023-03-09
19 | 2023-03-17 | Fully Written Operation Manual | Ibrahim | Complete | 2023-03-17
20 | 2023-03-24 | Completion of Evidence Manual | Ibrahim | Complete | 2023-03-24
21 | 2023-03-24 | Revise and Print Poster | Megan | Complete | 2023-03-24
22 | 2023-03-28 | Design Presentation | All | Complete | 2023-03-28
23 | 2023-04-01 | Senior Design Day | All | Incomplete | Incomplete
24 | 2023-05-01 | Final Exams Begin | All | Incomplete | Incomplete
25 | 2023-05-06 | Graduation | All | Incomplete | Incomplete