## Sheet1
Spring Project Plan
Milestones and Deliverables | Goal Completion Date | Status | Date Completed
Finalize Testing Apparatus | 2024-01-12 | Incomplete
Finalize Testing Procedure | 2024-01-12 | Incomplete
Finalize Implantation Method | 2024-01-12 | Incomplete
Sponsor Meeting | 2024-01-12 | Incomplete
Martin Luther King, Jr. holiday | 2024-01-15 | Incomplete
Begin Testing | 2024-01-16 | Incomplete
Sponsor Meeting | 2024-02-04 | Incomplete
Poster Draft 2 | 2024-02-14 | Incomplete
VDR4 | 2024-02-15 | Incomplete
VDR5 | 2024-02-29 | Incomplete
Modify Any Testing Equipment | 2024-03-01 | Incomplete
Modify Any Testing Procedures | 2024-03-01 | Incomplete
Sponsor Meeting | 2024-03-01 | Incomplete
Spring Break | 2024-03-09 | Incomplete
| 2024-03-17 | Incomplete
Complete Testing | 2024-03-18 | Incomplete
Poster Draft 3 | 2024-03-18 | Incomplete
VDR6 | 2024-03-21 | Incomplete
Complete Testing | 2024-03-22 | Incomplete
Evidence Manual | 2024-03-22 | Incomplete
Document Testing Results | 2024-03-22 | Incomplete
Final Poster | 2024-03-25 | Incomplete
Finalize CAD | 2024-03-28 | Incomplete
Finalize Design | 2024-03-29 | Incomplete
Design Day Preparation | 2024-03-29 | Incomplete
Sponsor Meeting | 2024-03-29 | Incomplete
Engineering Design Day | 2024-04-01 | Incomplete
Final Presentation | 2024-04-01 | Incomplete
Finals | 2024-05-03 | Incomplete
Graduation | 2024-05-04 | Incomplete