## Sheet1
Spring Project Plan
2024-01-07
2024-01-08
2024-01-09
2024-01-10
2024-01-11
2024-01-12
2024-01-13
2024-01-14
2024-01-15
2024-01-16
2024-01-17
2024-01-18
2024-01-19
2024-01-20
2024-01-21
2024-01-22
2024-01-23
2024-01-24
2024-01-25
2024-01-26
2024-01-27
2024-01-28
2024-01-29
2024-01-30
2024-01-31
2024-02-01
2024-02-02
2024-02-03
2024-02-04
2024-02-05
2024-02-06
2024-02-07
2024-02-08
2024-02-09
2024-02-10
2024-02-11
2024-02-12
2024-02-13
2024-02-14
2024-02-15
2024-02-16
2024-02-17
2024-02-18
2024-02-19
2024-02-20
2024-02-21
2024-02-22
2024-02-23
2024-02-24
2024-02-25
2024-02-26
2024-02-27
2024-02-28
2024-02-29
2024-03-01
2024-03-02
2024-03-03
2024-03-04
2024-03-05
2024-03-06
2024-03-07
2024-03-08
2024-03-09
2024-03-10
2024-03-11
2024-03-12
2024-03-13
2024-03-14
2024-03-15
2024-03-16
2024-03-17
2024-03-18
2024-03-19
2024-03-20
2024-03-21
2024-03-22
2024-03-23
2024-03-24
2024-03-25
2024-03-26
2024-03-27
2024-03-28
2024-03-29
2024-03-30
2024-03-31
2024-04-01 | Project Complete
2024-04-02
2024-04-03
2024-04-04 | Eng. Design Day
2024-04-05
2024-04-06
2024-04-07
2024-04-08
2024-04-09
2024-04-10
2024-04-11
2024-04-12
2024-04-13
2024-04-14
2024-04-15
2024-04-16
2024-04-17
2024-04-18
2024-04-19
2024-04-20
2024-04-21
2024-04-22
2024-04-23
2024-04-24
2024-04-25
2024-04-26
2024-04-27
2024-04-28
2024-04-29
2024-04-30
2024-05-01
2024-05-02
2024-05-03
2024-05-04 | Graduation

## Sheet2
WBS NUMBER | TASK TITLE | DESCRIPTION | TASK SUBMITTER | DURATION (# of Days) | Date
1 | FD | Finalize Design | All | 3 | 1/9/24-1/11/24
2 | EBOM | Expand on Bill of Materials | Matt | 2 | 1/16/24-1/17/24
3 | BOC | Begin Ordering Components | Matt | 1 | 2024-01-18
4 | CNT | Attain and Test NASA's Carbon Nanotube Filter from Gary | All | 1 | 2024-01-22
5 | CW | Create Website | Kencin | 4 | 1/22/24 - 1/25/24
6 | IPT | Initial Prototype Testing and Simulation | All | 1 | 2024-01-26
7 | VDR 4 | VDR 4 | Lily | 3 | 1/29/24 - 1/31/24
8 | PPP | Prepare Posters 2 and 3 | Lily | 5 | 2/5/24 - 2/9/24
9 | VDR 5 | VDR 5 | Tim | 3 | 2/13/24 - 2/15/24
10 | FBM | Finalize Bill of Materials | Matt | 3 | 2/14/24 - 2/16/24
11 | OFC | Order Final Components | Matt | 1 | 2024-02-16
12 | FPT | Final Prototype Testing | All | 2 | 3/4/24 - 3/5/24
13 | Final PRO | Final Prototype | All | 1 | 2024-03-18
14 | FEM | Finalize Evidence Manual | Kencin | 2 | 3/21/24 - 3/22/24
15 | EDDP | Engineering Design Day Poster Completed | Lapadre | 3 | 3/18/24 - 3/20/24
16 | PEDD | Prepare and Practice for Engineering Design Day Presentation | All | 4 | 3/26/24 - 3/29/24
17 | ENGD | Engineering Design Day | All | 1 | 2024-04-01
18 | SFF | Study for Finals | All | 5 | 4/22/24 - 4/26/24
19 | Final | Final Exam Week | All | 5 | 4/29/24 - 5/3/24
20 | Graduation | Leave This God Forsaken Place | All | 1 | 2024-05-03