## Sheet1
PROJECT
FAMU/FSU COE Team 522 Senior Design 2024 |  |  | Note: Important Dates --------------------------------------------------------->
SPONSOR
Rockwell Automation
Project Schedule/Task List
WBS # | ASSIGNMENT | TASKS | TASK OWNER | START DUE | DUE DATE | PROGRESS
1 | Acquire Hardware/Software |  |  | 2024-02-06 | 2024-02-18
1.1 |  | Order Parts: Finalize BOM and order materials/hardware | All |  |  | 100%
1.2 |  | Emulate 3D Training | All |  |  | 100%
1.3 |  | CAD for individual components | Caleb |  |  | 100%
1.4
1.5
2 | Emulate 3D & CAD Model |  |  | 2024-02-19 | 2024-02-25
2.1 |  | CAD full system | Caleb, Maria |  |  | 90%
2.2 |  | Finalize order of Rockwell materials with Dr. McConomy | Caden |  |  | NA | Important Dates
2.3 |  | Proof of concept (dye movement, material ejection, "slide" for design input) | Luis, Chloe |  |  | 75%
2.4 |  | Compile motor control code (Map I/O) | Caden |  |  | 100% |  | Title | Due Date
2.5 |  | Continue developing digital twin in Emulate 3D. | All |  |  | 50% |  | Design Review 5 (DR5) | 2024-02-27 | 100%
3 | Prefabrication |  |  | 2024-02-26 | 2024-03-03 |  |  | Final Abstract | 2024-02-23 | 100%
3.1 |  | Test electronics components (drivers, motors, power supply, wiring) | Caden, Luis |  |  | 100% |  | Poster(peer review) | 2024-02-27 | 100%
3.2 |  | Continue developing digital twin in Emulate 3D. Virtual assembly | All |  |  | 25% |  | Web Page Update | 2024-03-01 | 100%
3.3 |  | Parts to machine shop (Gantry plate, Aluminum rods, Dye mold) | Caleb |  |  | 100% |  | DR5 Presentation | 2024-03-07 | 100%
3.4 |  | Start building physical prototype | All |  |  | 100% |  | Risk Assesment | 2024-03-08 | 100%
3.5 |  | Test/troubleshoot motor controller code | Caden, Maria |  |  | 80% |  | Design Review 6 (DR6) | 2024-03-19
4 | Assembly |  |  | 2024-03-04 | 2024-03-10 |  |  | Engineering Design Day - Poster | 2024-03-25
4.1 |  | Continue physical prototype assembly | All |  |  | 50% |  | DR6 Presentation | 2024-03-28 |  | invite sponsors**
4.2 |  | Wiring/Soldering of all necessary electronic components | Caden |  |  | 100% |  | Operation Manual | 2024-03-29
4.3 |  | Assemble electronic components to other material supports | Luis |  |  | 25% |  | Validation/Conference Paper | 2024-04-01
4.4 |  | Start physical prototype manual testing | Maria |  |  | 70% |  | Senior Design Day - Presentation | 2024-04-04
4.5 | [7 empty] | Web Page Final | 2024-04-04
5 | Testing |  |  | 2024-03-11 | 2024-03-17 |  |  | Final Report | 2024-04-19
5.1 |  | Test automated and manual components of system | Maria |  |  | 50% |  | Final System Demonstration | 2024-04-26
5.2 |  | Debug and redesign to fix any problems that arise in testing | All |  |  |  |  | Final Exams | 2024-04-29
5.3 |  | New parts if needed (3D print) | Caleb |  |  | 80%
5.4 |  | Continue trouble shooting and work to finalize prototype design | All
5.5
6 | Test/Assemble |  |  | 2024-03-18 | 2024-03-24
6.1 |  | Finalize digital twin in Emulate 3D | All |  |  | 50%
6.2 |  | Develop retention quiz for project targets | Luis, Chloe
6.3 |  | Reassemble and test physical system with finalized design | Maria, All
6.4 |  | repeat steps 5.1, 5.2, and 6.3 | All
6.5
7 | Final Assembly |  |  | 2024-03-25 | 2024-03-31
7.1 |  | Work to finish both digital twin in Emulate 3D and prototype | All
7.2
7.3
7.4
7.5 |  | DONE with Emulate 3D model | All
8 |  |  |  | 2024-04-01 | 2024-04-07
8.1 |  | Prepare for senior design day and final presentation | All | 2024-04-01
8.2 |  | DONE with physical protoype | All |  | 2024-04-04
8.3 |  | Senior Design Day Presentation/Demo | All |  | 2024-04-04